## Sheet1
Sr. No. | SPV | Issue | Brief Description | Remark | Next Steps as on 7 July 2026
1 | SS6PL | INOX- Raiberally | Consumption of the customer has reduced drastically, against PPA capacity and current shareholding. Risk of captive status breach | As per Kartikeya's email dated 6 July 2026, we should curtail generation to the extent of shortfall in demand from the customer and bill the customer on deemed generation, in no case should there be a situation of captive breach | Nitin to take this up Sanjay Sadashiv
2 | SS6PL | JSL | Consumption of the customer has reduced drastically, against PPA capacity and customer requesting reduced injection to avoid lapsation | As per discussion dated 27th June 2026, we should curtail generation to the extent of shortfall in demand from the customer and bill the customer on deemed generation, in no case should there be a situation of captive breach. Further, banking agreement of customer is expected to be signed by 15th July 2026, currently pending for BG verification from Discom due to delayed response from customer's bank and final approval from Chairman UPPCL | Vinod Sir to take this up with the customer.
3 | NREPL | INOX- Surajpur | Consumer requesting schedule of only 2.3 MW against PPA capacity of 4.2 MW till the execution of Banking agreement under LTOA | As per Ishan and Nitin's discussion, CO team to sell this power under alternate mechanism, however, any breach of captive status to be appropriately highlighted to the customer. | Nitin to take this up Sanjay Sadashiv
4 | SS7PL | Ultratech Transaction | LTOA-Consumer to revise connectivity agreements (UPPTCL) STOA-Re-estimation of UTCL solar consumption capacity (without banking) Consumer to provide ST-11 NOCs and bear statutory cost | LTOA-Sunsure is providing consultancy support on interim basis. Consultancy charges shall be reimbursed by UltraTech STOA - the customer has declined to bear approval costs. Estimated statutory charges (for 4 months STOA power delivery) are ~₹6.24 lakh and consultancy charges ~₹4 lakh. CSS shall be applicable on the customer during the STOA period and reimbursed after captive status is achieved at the end of the financial year. | Vinod Sir to take this up with the customer.
5 | SS6PL (New Capacity - 6.2 MW) | WC Aligarh | PPA SCOD is 6 August 2026. LT-2 approval has been obtained; however, timely power supply through the LTOA route is unlikely. The customer is unwilling to procure power through STOA. | Consumer is unwilling to procure power from Sunsure through STOA, citing lower IEX prices. Request extension under PPA Clause 3.4 (up to six months) by highlighting approval delays. This will safeguard the SCOD timeline and provide flexibility for interim third-party transactions. | Vinod Sir to take this up with the customer.
6 | SS6PL (Old Capacity - 6.67 MW) | WC Aligarh | LD charges raised for ~16 lakh FY 24-25 | The customer is being requested to reassess the delay impact considering the actual energy supplied, as surplus energy was delivered beyond the contractual obligation despite the delay. | CO team to engage with the customer, with support from the BD team during discussions.
7 | SS8PL | Hilltop Capacity Operationalization | A 2.5 MW capacity has been tied up with Hilltop and the BPTA has been executed. The customer now intends to surrender the LTOA. | Since the BPTA has already been executed, relinquishment charges will be applicable if the customer proceeds with surrendering the LTOA. | Amritesh to take this up with the customer.
8 | SS5PL | CHW Forge -Energy Settlement Payments | Payment stuck ~ Rs. 14 lakhs against Feb 26 and March 26 invoices, as CHW denied to pay for lapsed units as per OA bill | Explained CHW officials about the reason i.e. due to less consumption of CHW's facility and communicated to relaese the full funds | CHW to revert back after internal reconicaltion
9 | MH All SPVs | LTOA
10 | SS31PL | Apollo/ Kisan Moulding Pending Payment | Outstanding since Jan 26(Apollo Tubes) and Feb-26(Kissan Mouldings) | Capacities reduced, PPA amedments signed, waiting for approvals | Paurush to take this up with consumer post approvals
11 | SS26PL | Wonder Cement LD | LD charges raised for ~22 lakh FY 25-26 | The customer is being requested to reassess the delay impact considering the actual energy supplied, as surplus energy was delivered beyond the contractual obligation despite the delay. | CO team to engage with the customer, with support from the BD team during discussions.
14 | Tamil Nadu | JSA Billing | Billing pending for May 26 | To decide the tariff for invoicing JS Auto considering the LD issue